## Sheet1
PG Full Stack Web Development
PROJECT FOR PHASE 1
TYPE OF ACTIVITIES | PLAN DURATION (DAY)
ANALYSIS | 5 DAYS
WRITING CODE | 5 DAYS
TESTING THE SOFTWARE | 3 DAYS
DOCUMENTATION | 2 DAYS
START DAY | END DAY | ACTIVITIES DESCRIPTION | PERSON IN CHARGE
2023-01-01 | 2023-01-05 | Analysis the system requirement | Project leader
2023-01-06 | 2023-01-10 | Prepare the system specification | Project leader
|  | Writing the code | Programmer
2023-01-11 | 2023-01-13 | Testing the software | Quality Assurance team
2023-01-14 | 2023-01-15 | Writing the documentation | Quality Assurance team